## Summary
LMNS Equity and Equality Action Plan: Northamptonshire LMNS
Executive Summary | This action plan reflects the health inequalities priorities described in the 2021/22 priorities and operational planning guidance: Implementation guidance, and sets out how the Northamptonshire LMNS will implement the ambitions and priority areas given to help achieve equity and equality for all mothers and babies in Northamptonshire.
Action Plan Contents | Vision, Values & Aims
Priority 1
Priority 2
Priority 3
Priority 4a
Priority 4b
Priority 4c
Priority 4d
Priority 4e
Priority 5
Communication Plan

## Vision
Vision
Overall Vision | The government’s national maternity safety strategy sets out an ambition, by 2025, to halve rates of stillbirths, neonatal and maternal deaths and brain injuries during or soon after birth and to reduce the rate of preterm births from 8% to 6%. To achieve the ‘halve it’ ambition, it is important to improve outcomes for those groups most at risk. It is recognised that different populations have different risk and protective factors and therefore different approaches are needed for different populations. In order to improve equity and equality in maternity and neonatal care, it is first imperative that interventions are targeted at groups of women and families within the community who are more likely to experience poorer outcomes. Northamptonshire Local Maternity & Neonatal System (LMNS) comprises of two Unitary Councils (North and West Northamptonshire) one CCG, two acute trusts, a community and mental health trust and the local authorities, all who commission or provide maternity services to the families of Northamptonshire. The ambitions and priority areas given within this action plan are co-produced by those within the LMNS, and will help guide our work and refresh our approach to help achieve equity and equality for all mothers and babies in Northamptonshire.
Values | Value | Rationale | Key Actions
| Collaboration | co-ordinated effort across many stakeholders, especially to tackle the social determinants of health | This is the National Vision
| Co-production | Interventions are more likely to be culturally and socially relevant and clinically effective if parents and staff work in partnership to improve clinical quality. | This is the National Vision
| Proportionate universalism | To ‘raise and flatten’ the inequalities gradient, universal action is needed with a scale and intensity that reflects need | This is the National Vision
Aims | equity for mothers and babies from Black, Asian and Mixed ethnic groups and those living in the most deprived areas
race equality for staff
ICS Interdependencies | Working Collaboratively across the system
CYP Transformation Programme, Perinatal Mental Health Transformation Programme, Digital Transformation ProgrammeProvider Trusts, Voluntary Sector
People Plan

## Priority 1
Priority 1: Restore NHS Services Inclusivity
Description | [7 empty] | Process indicator
At national level, the decline in access among some groups during the first wave of the pandemic broadly recovered in later months. Some pre-existing disparities in access, experience and outcomes have widened during the pandemic. | [7 empty] | Implementation of the COVID-19 four actions
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
Priority 1 Restore NHS services inclusively – with a focus on ethnicity and deprivation. Continue to implement the COVID-19 four actions. | Ensure clinicians have a lower threshold to review, admit and consider multidisciplinary escalation in women from ethnic minority groups. | 1.1 | Ensuring that all trusts have implemented and are using COVID-19 guidelines in line with national recommendations | Ensure Trust guidance reflects the need for additional support for women identified as being at more risk of poorer outcomes | Trusts LMNS PMO Team | Quality Surveillance |  | Regular review dates on guidance | All trusts have guidelines inline with national recommendations
|  | 1.2 | To confirm the vaccination process with each trust, ensuring that at risk- women are offered vaccinations | Continue promotion of vaccination, ensuring every contact counts | LMNS PMO Team | Quality Surveillance |  | Regular review of process Quarterly vaccination uptake data | Vaccination hubs were set up during height of pandemic.
| Reach out and reassure pregnant BAME women with tailored communications. | 1.3 | Tailored communication to reassure pregnant women from Black, Asian and Mixed ethnic groups |  | LMNS PMO Team Trusts MVP | Quality Surveillance |  | Regular review of iinformation to ensure up to date Up to date information to be included on Trust's and LMNS website | Kettering General Hospital - COVID-19 Information Leaflet for Black, Asian and Mixed Ethnic Groups Northampton General Hospital – COVID 19 Information Leaflet for Black, Asian and Mixed Ethnic Groups Updated information on both Trusts websites | [8 empty] | Q2 2025/26+AA4:AV4
|  | 1.4 | To promote resources and translations via Maternity staff | use of services | Trusts | Quality Surveillance |  | Confirmation that translation services are being used Feedback from user groups | Both Trusts using translation services
|  | 1.5 | MVP Feedback | MVP Q & A Sessions User Surveys LMNS Website updates | MVP LMNS PMO Team | Quality Surveillance |  | Feedback from users MVP Report to LMNS Programme Board
| Ensure hospitals discuss vitamins, supplements and nutrition in pregnancy with all women. | 1.6 | Importance of folic acid is discussed and recorded in the maternity records | Audit maternity records to ensure vitamins, supplements and nutrition is discussed in pregnancy | Trusts LMNS PMO Team | Promoting Good Practice for Safer Care |  | MSDS data Audit of records User feedback | Both Trusts have a midwife who leads on healthy lifestyle in pregnancy and information on the importance of folic acid is discussed and recorded in the maternity records
|  |  |  | Interrogate local data to assess uptake of folic acid by ethnic group as we cannot currently extract this data through the Maternity Information System (MIS) | Trusts LMNS PMO Team | Promoting Good Practice for Safer Care |  | Audit report to PGPSC Group Report to LMNS Programme Board
|  |  |  | Continue to work with MIS provider to develop ability to capture and extract the data | Trusts LMNS Digital Lead | Digital Workstream |  | Reports to LMNS Digital Group Reports to ICB Digital Transformation Board
|  |  |  | Business case to procure new MIS provider as part of the Maternity Digital Strategy | Trusts LMNS PMO Team | Digital Workstream |  | Reports to LMNS Programme Board Reports to ICB Digital Transfromation Board
|  | 1.7 | Importance of vitamins discussed with all women. Women with darker skin are recommended to take Vitamin D | Ongoing targeted information, including use of folic acid, vitamin D and vaccinations Continue to work with MIS provider to develop ability to capture and extract the data Business case to procure new MIS provider | Trusts MVP LMNS PMO | Quality Surveillance |  | MSDS data Audit of records User feedback
| Ensure all providers record on maternity information systems the ethnicity of every woman, as well as other risk factors, such as living in a deprived area (postcode), co-morbidities, BMI and aged 35 years or over, to identify those most at risk of poor outcomes. | 1.8 | To ensure that all reporting is in line with national requirements and ensure robust reporting pathways | Ongoing monitoring of national reporting requirements | Digital Midwives | Digital Workstream |  | MSDS data CNST Compliance
|  | 1.9 | Data collection review on MSDS submission | Continue to work with MIS provider to develop ability to capture and extract the data | Digital Midwives | Digital Workstream |  | MSDS data compliance | Both Trusts have made significant improvements in the recording of this information. The MSDS raw data for December 2021
|  |  |  | Business case to procure new MIS provider as part of the Maternity Digital Strategy | Trusts LMNS PMO | Digital Workstream |  | Reports to LMNS Programme Board Reports to ICB Digital Transfromation Board

## Priority 2
Priority 2: Mitigate against digital exclusion
Description | [7 empty] | Process indicator
Systems are asked to ensure that: • providers offer face-to-face care to patients who cannot use remote services • more complete data collection is carried out, to identify who is accessing face-to-face, telephone or video consultations, broken down by relevant protected characteristic and health inclusion group • they take account of their assessment of the impact of digital consultation channels on patient access. | [7 empty] | The number of women with a Personalised Care and Support Plan which covers: o antennal care by 17 weeks' gestation o intrapartum care by 35 weeks' gestation o postnatal care by 37 weeks' gestation The numbers of women who had all three of the above in place by the gestational dates All indicators are available with breakdowns by ethnicity and index of multiple deprivation (source: MSDS)
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
Priority 2 Mitigate against digital exclusion | Ensure that providers offer face-to-face care to patients who cannot use remote services | 2.1 | Further work required to identify geographical areas of limited connectivity, identification of families without connectivity due to access or cost and those who are unable to access information | Recruitment of ICB LMNS Digital Lead | LMNS PMO Team | LMNS Programme Board
|  |  |  | Scope out the extent of digital exclusion in the County | ICB LMNS Digital Lead | Digital Transformation |  | Digital Workstream reports LMNS Programme Board reports
|  | 2.2 | Maternity services to ensure birthing people who are unable to use remote services are identified at booking and face-face-face care is provided | ICB LMNS Digital lead to work with the maternity services to implement process | ICB LMNS Digital Lead Trusts | Digital Transformation |  | Audit of compliance Digital Workstream reports
| Ensure that more complete data collection is carried out, to identify who is accessing face-to-face, telephone or video consultations, broken down by relevant protected characteristic and health inclusion group | 2.3 | Not currently captured | ICB LMNS Digital lead to work with the maternity services to implement process | ICB LMNS Digital Lead Trusts | Digital Transformation |  | Audit of compliance Digital Workstream reports
| Ensure providers take account of their assessment of the impact of digital consultation channels on patient access. | 2.4 |  | Monitor triangulated Trust data to ensure that birthing people are able to access care | ICB LMNS Digital Lead | Digital Transformation |  | Audit of compliance Digital Workstream reports
| Ensure personalised care and support plans (PCSPs) are available in a range of languages and formats, including hard copy PCSPs for those experiencing digital exclusion | 2.5 | PCSPs have been co-produced and are available in hard copy or to download for all women. They are also available in the 5 top languages spoken in Northamptonshire | Co-produce revised personalised care and support plans with service users, ensuring feedback is captured and making changes where needed | LMNS PMO Team MVP | Promoting Good Practice for Safer Care |  | Use of PCSPs User feedback
|  | 2.6 |  | Audit of 5% of records to ensure that PCSPs are being offered | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | Audit results PGPSC Reports
|  | 2.7 |  | Educate staff about the importance of personalised care and support plans | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | Training records / plans Information on LMNS website
|  | 2.8 |  | Ensure personalised care and support plans are available in a range of languages and other accessible formats including versions for birthing people with hearing and sight loss and those with Learning disabilities | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | PCSPs available in different languages, narrated and sub titled videos and pictorial versions
|  | 2.9 |  | Pilot Patient Knows Best which interfaces to the NHS App and supports patient views of their record and communication channels | ICB Digital Lead Trusts | Digital Transformation
|  | 2.1 |  | Develop and upload videos to the LMNS website, explaining what a personalised care and support plan is and how to use them | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | Information on LMNS Website

## Priority 3
Priority 3: Ensure datasets are complete and timely
Description | [7 empty] | Process indicator
Systems are asked to continue to improve the collection and recording of ethnicity data. NHS England and NHS Improvement will support the improvement of data collection, including through the development of the health inequalities improvement dashboard. | [7 empty] | Safety action 2, category 9: data submitted to Maternity Services Data Set (MSDS) contains valid postcode for mother at booking in 95% of women booked in the month. • Ethnicity data quality (source: Regional Measures Report). • Safety action 2, category 10: data submitted to MSDS includes a valid ethnic category for at least 80% of the women booked in the month. Not stated, missing and not known are not valid records.
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
Priority 3: Ensure datasets are complete and timely to continue to improve the collection and recording of ethnicity datal exclusion | Improve data quality by ensuring 95% of records contain a valid postcode and 80% of records have a valid ethnicity | 3.1 | Both Trusts and the LMNS continue to monitor the submission of the MSDS information in line with the CNST Safety Action | Data collection review on MSDS submission | ICB and LMNS Digital Lead Trusts | Digital Transformation |  | MSDS submission LMNS Programme Board
| Use data to identify and inform birthing people and staff when planning care pathways and discussing personalised care and support plans | 3.2 | Dependant on manual work as current clinical systems do not support more granular data outputs | Develop system wide business case to procure new Clinical IT system | ICB Digital Programme Lead LMNS PMO Trusts | Digital Transformation |  | Completion of business case
|  | 3.3 |  | Continue to work with current IT system supplier to improve functionality | Trusts | Digital Transformation |  | Digital Transformation Group reports
|  | 3.4. |  | Enhanced data collection to breakdown ethnicity into subgroups | Trusts | Digital Transformation |  | Digital Transformation Group reports | Dependant on manual work as current clinical systems do not support more granular data outputs
|  | 3.5 |  | Triangulate data to include age, ethnicity plus areas of deprivation for stillbirths, low birth weight babies and pre-term babies | LMNS PMO Trusts | Digital Transformation |  | Digital Transformation Group reports | Dependant on manual work as current clinical systems do not support more granular data outputs
|  | 3.6 |  | Source more recent data for maternal obesity (current findings based on 2017) | /Trusts' Digital Leads/BI/LMNS Programme Support Officer | Digital Transformation |  | Digital Transformation Group reports | Dependant on manual work as current clinical systems do not support more granular data outputs
|  | 3.7 |  | Recruit LMNS Programme Support Officer, who will support data analysis until such time as the Maternity Clinical IT system functionality is improved | LMNS PMO | Digital Transformation |  | LMNS Programme Board
|  | 3.8 |  | Current local information relating to obesity data needs to be broken down by age, ethnicity and deprivation. Health & Wellbeing Midwives from each Trust to develop a data capture process to achieve this, in conjunction with Trust Digital leads in maternity servcies . | Trusts Digital Leads/LMNS Programme Support Officer | Digital Transformation |  | Digital Transformation Group reports
|  | 3.9 |  | Triangulate data for complex social needs with women and birthing people over 40 and under 20 years | LMNS Programme Lead | Digital Transformation |  | Digital Transformation Group reports
|  | 3.10 |  | Identify smoking rates by country of birth to support targeted interventions | BI/LMNS Programme Support Officer | Digital Transformation |  | Digital Transformation Group reports

## Priority 4a
Priority 4a: Accelerate preventative programmes that engage those at greatest risk of poor health outcomes, Understand your population and co-produce interventions
Description | [7 empty] | Process indicator
• Understand the local population – its health outcomes and community assets. • Understand staff experience, using Workforce Race Equality Scheme data. • Use this understanding to plan co-production activity to design interventions to improve equity for women and babies and race equality for staff.
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
Priority 4: Accelerate preventative programmes that proactively engage those at greatest risk of poor health outcomes | Understand the local population’s maternal and perinatal health needs (including the social determinants of health). | 4a1.1 |  | Complete Equity & Equality Analysis | LMNS PMO MVP | LMNS Programme Board |  | LMNS Programme Board reports | Initial Health Needs Analysis complete, however, more in-depth data and analysis is required to identify health inequalities experienced by those with other protected characteristics and for inclusion groups.
|  | 4a1.2 |  | Recruit an LMNS Equality & Diversity Lead to implement targeted work and assist in understanding of the health needs of the local population | LMNS PMO | LMNS Programme Board |  | LMNS Programme Board reports
|  | 4a1.3 |  | Recruit MVP Equality & Diversity Champion | LMNS PMO MVP | MVP |  | LMNS Programme Board reports
| Map the community assets which help address the social determinants of health. | 4a1.4 |  | Identify and map out community organisations who are able to support and enhance the health and wellbeing of women and families in Northamptonshire | LMNS PMO | LMNS Programme Board |  | LMNS Programme Board reports
|  | 4a1.5 |  | Further scope community organisations active in maternity area providing support /promoting health and wellbeing | LMNS PMO MVP | LMNS Programe Board |  | LMNS Programme Board reports
| Understand staff experience, using Workforce Race Equality Scheme data | 4a1.6 |  | Baseline WRES assessment of the experience of staff by ethnicity included in the Quity and Quality Analysis | LMNS PMO Trusts | LMNS Programme Board |  | LMNS Programme Board reports
|  | 4a1.7 | National WRES data collected and submitted by Trusts needs further analysis to break information into departments / services / staff groups to enable the clear identification of maternity/neonatal staff responses | LMNS Equality & Diversity Lead to carry out survey of maternity and neonatal staff using Workforce Race Equility Scheme indicators | LMNS PMO Trusts | Workforce |  | Workforce reports LMNS Programme Board reports
|  | 4a1.8 |  | Expand workforce support to staff with disabilities, health issues or similar to support a diverse workforce | LMNS PMO Trusts | Workforce |  | Workforce reports LMNS Programme Board reports

## Priority 4b
Priority 4b: Accelerate preventative programmes that engage those at greatest risk of poor health outcomes Action on maternal mortality, morbidity and experience
Description | [7 empty] | Process indicator
LMNS are asked to ensure equity in access, experience and health outcomes for women from Black, Asian and Mixed ethnic groups and those women living in the most deprived areas. They may consider other protected characteristics and inclusion groups. | [7 empty] | The Maternal Medicine Network is implementing the KPIs in the nonmandatory national service specification. They are broken down by level of deprivation of the mother’s postcode and ethnicity • Booking at <70 days gestation (source: Regional Measures Report) • Proportion of women with complex social factors who attend booking by 10 weeks, 12+6 weeks and 20 weeks (source: Regional Measures Report) • For each complex social factor grouping, the number of women who: attend for booking by 10, 12+6 and 20 weeks; and attend the recommended number of antenatal appointments • % of parent members of the MVP who are from ethnic minority groups • % of women attending the booking appointment who are from ethnic minority groups (source: Regional Measures Report) • Ethnicity data quality (source: Regional Measures Report)
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
Priority 4: Accelerate preventative programmes that proactively engage those at greatest risk of poor health outcomes | Implement maternal medicine networks to help achieve equity | 4b.1 | Collaboration with LLR Maternal Medicine Network | Implementation of pathways | UHL | LMNS Programme Board |  | Pathways in place Monitoring of referrals and activity
| Offer referral to the NHS Diabetes Prevention Programme to women with a past diagnosis of gestational diabetes mellitus (GDM) who are not currently pregnant and do not currently have diabetes. | 4b.2 |  | Understand the process needed to adjust the current NHS Diabetes Prevention Programme pathway to include women with a past diagnosis of GDM, who are not currently pregnant | LMNS CD | Prevention
|  | 4b.3 |  | Explore the opportunities with wider maternity services partners to provide access to a preconceptual programme of education for BAME women and birthing people | LMNS PMO Team | LMNS Programme Board |  | Prevention workstream reports Diabetes Transformation reports
|  | 4b.3 |  | Co-produce and new tailored communication with MVPs and community groups | LMNS PMO Team MVP | LMNS Programme Board |  | Co-produced information in a variety of formats and in the common languages used within the County
| Implement NICE CG110 antenatal care for pregnant women with complex social factors | 4b.4 | Actions to increase booking by 10 weeks for: - women and birthing people under 20 years - Black or black British women and birthing people - women and birthing people in bottom 20% deprivation - women and birthing people with complex social factors - explore perinatal mental health provision more robustly | Understand barriers to booking through focus groups, work with MVP, "Who's shoes" | LMNS PMO Team MVP | Promoting Good Practice for Safer Care |  | Output from Whose Shoes and focus groups LMNS Programme Board reports
|  |  |  | Targeted communication to women and birthing people where English is not their first language - women and birthing people under 20 years - women and birthing people over 40 years - Asian or Asian Black British women and birthing people | LMNS PMO Team MVP | LMNS Programme Board |  | Targeted information available on LMNS website in various formats and languages User feedback
|  | 4b.5 |  | Complex Social needs: Triangulate data for complex social needs with women and birthing people over 40 and under 20 years. | LMNS PMO Team | Promoting Good Practice for Safer Care |  | Baseline Data Spot Check audits | The Maternity Clinical IT system currently does not support the submission of information to enable further analysis for each complex social factor grouping, or the number in each complex social factor grouping. Manual reports should therefore be run, with spot check audits to obtain baseline data
|  | 4b.6 |  | Breastfeeding rates - targeted support for women and birthing people in areas of deprivation. Peer support programme in areas of high deprivation | LMNS PMO Team | Prevention |  | Prevention workstream reports Annual report - LMNS Programme Board | Programme "Milk and You" in place in Corby and Daventry, starting in Wellingborough and Northampton
|  | 4b.7 | Smoke free pregnancies | Benchmark current service provision against the NHS Maternity Tobacco Model to identify the areas of improvement needed | Prevention Lead | Prevention |  | Prevention workstream reports
|  | 4b.8 |  | Identify Country of birth for women who are smoking at the time of the booking appointment to enable targeted support | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | Audit results PGPSC Reports
|  | 4b.9 |  | Employ Maternity specific Tobacco Dependency Advisors | Prevention Lead Trusts | Prevention |  | Post holders in place | Recruitment difficulties
|  | 4b.10 |  | Explore use of incentive schemes and direct supply nicotine replacement therapy | LMNS PMO Team Prevention Lead Trusts | Prevention |  | Prevention reports LMNS Programme reports
| Implement maternal mental health services with a focus on ethnicity and deprivation. | 4b.11 |  | Benchmark current service provision against the maternal mental health service model to identify the areas of service development required | Perinatal Mental Health Services Lead Trusts | Perinatal Mental Health |  | LMNS Programme reports
|  | 4b.12 |  | Ensure staff training and parent education and support is co-produced and tailored to local needs | LMNS PMO Team Perinatal Mental Health Services Lead Trusts MVP | Perinatal Mental Health LMNS Programme Board |  | Pre and post training measures LMNS Programme Board reports User feedback
|  | 4b.13 |  | DadPad available to all partners / fathers to support looking after mental health | LMNS PMO Team MVP | Promoting Good Practice for Safer Care |  | Audit data User feedback
|  | 4b.14 |  | Develop and upload videos to the LMNS website, explaining what a personalised care and support plan is and how to use them | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | Information on LMNS Website
| Ensure the MVPs in your LMS reflect the ethnic diversity of the local population, in line with NICE QS167 | 4b.15 |  | MVP meetings and drop in sessions to be organised in a variety of locations in order to encourage membership from all areas of the community | MVP | LMNS Programme Board |  | MVP reports to LMNS Programme Board
|  | 4b.16 |  | Recruitment of an MVP Diversity Champion | MVP LMNS PMO Team | LMNS Programme Board |  | MVP reports to LMNS Programme Board

## Priority 4c
Priority 4c: Action on perinatal mortality and morbidity
Description | [7 empty] | Process indicator
LMS are asked to address the leading causes of perinatal mortality and morbidity for babies from Black, Asian and Mixed ethnic groups and born to women living in the most deprived areas. LMS may consider other protected characteristics and inclusion groups. | [7 empty] | Process indicators Outcome indicators • Placement on a continuity of carer pathway – Black/Asian women • Placement on a continuity of carer pathway – women living in the most deprived areas • Baby Friendly accreditation Outcome Indicators Breast milk at first feed • Low birth weight (<2,500g for term births) • Deliveries under 27 weeks • Deliveries under 37 weeks
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
Priority 4: Accelerate preventative programmes that proactively engage those at greatest risk of poor health outcomes | Implement targeted and enhanced continuity of carer, as set out in the NHS Long Term Plan. This means that, as continuity of carer is rolled out to most women, women from Black, Asian and Mixed ethnic groups and women living in deprived areas are prioritised, with 75% of women in these groups receiving continuity of carer by 2024. It also means ensuring that additional midwifery time is available to support women from the most deprived areas. | 4c.1 | CoC target removed by NHSEI to prioritise for roll out in the highest areas of Black, Asian and Mixed ethnicity populations | MCoC teams have been prioritised for roll out in the highest areas of Black, Asian and Mixed ethnicity populations and the postcodes of the lowest deciles as identified | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | CoC returns PGPSC Reports LMNS Programme Board reports
|  | 4c.2 |  | Develop Safe staffing risk assessment to inform roll out of further CoC teams | LMNS PMO Team Trusts | Workforce |  | Risk assessments completed quarterly Workforce group reports
|  | 4c.3 |  | Work with Trusts to ensure that women from Black, Asian, Mixed and minority ethnic backgraounds and those from the most deprived areas are prioritied for CoC | LMNS PMO Team | Promoting Good Practice for Safer Care |  | CoC returns PGPSC Reports LMNS Programme Board reports
|  | 4c.4 |  | Employ a Midwifery Recruitment and Retention Lead on a fixed term basis | LMNS PMO Team | LMNS Programme Board
|  | 4c.5 |  | Develop an LMNS workforce strategy that increased the number of midwives in Northamptonshire | LMNS PMO | Workforce |  | Recruitment strategy in place Reports to Workforce and LMNS Programme Board
| Implement a smoke-free pregnancy pathway for mothers and their partners. | 4c.6 |  | Benchmark current service provision against the NHS Maternity Tobacco Model to identify the areas of improvement needed | Prevention Lead | Prevention |  | Prevention workstream reports
|  | 4c.7 |  | Identify Country of birth for women who are smoking at the time of the booking appointment to enable targeted support | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | Audit results PGPSC Reports
|  | 4c.8 |  | Employ Maternity specific Tobacco Dependency Advisors | Prevention Lead Trusts | Prevention |  | Post holders in place | Recruitment difficulties
|  | 4c.9 |  | Smoking in pregnancy - Peer Support Programme | Prevention Lead Daventry Volunteers | Prevention
|  | 4c.10 |  | Explore use of incentive schemes and direct supply nicotine replacement therapy | LMNS PMO Team Prevention Lead Trusts | Prevention |  | Prevention reports LMNS Programme reports
| Implement an LMNS breastfeeding strategy and continuously improve breastfeeding rates for women living in the most deprived areas. | 4c.10 |  | Support providers and system partners in achieiving and maintaining BFI Accreditaiton and improving services in line with the BFI audit actions | LMNS PMO Team Trusts | Prevention |  | Prevention reports LMNS Programme reports
|  | 4c.11 |  | Develop and implement an LMNS Infant Feeding Strategy co-produced with MVP and service users | Prevention Lead Trusts MVP | Prevention |  | Prevention reports LMNS Programme reports
|  | 4c.12 |  | Implement targeted support for women and birthing people in areas of deprivation through provision of peer support programme | Milk & You (Daventry Volunteers) LMNS PMO | Prevention |  | Prevention reports Milk&You Annual Report LMNS Programme Board | Peer support programme funded by the LMNS

## Priority 4d
Priority 4d: Support for maternity and neonatal staff
Description | [7 empty] | Process indicator
LMS are asked to: • equip maternity and neonatal staff to provide culturally competent care • ensure maternity and neonatal staff experience race equality in the workplace | [7 empty] | • % of maternity and neonatal staff who attended training about cultural competence in the last two years • % of maternity and neonatal Serious Incidents relating to patient care with a valid ethnic code • % of Perinatal Mortality Review Tool cases with a valid ethnic code
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
Priority 4: Accelerate preventative programmes that proactively engage those at greatest risk of poor health outcomes | Roll out multidisciplinary training about cultural competence in maternity and neonatal services. | 4d.1 | Support cultural competency training across Northamptonshire | The LMNS to fund a 12-month subscription for all maternity and neonatal staff to have access to an online learning and sharing resource (All4Maternity), The resource includes 3 modules on cultural competence. | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | PGPSC Reports LMNS Programme Board reports
|  | 4d.2 |  | 6 cultural workshops facilitated by Baby Lifeline | LMNS PMO Team Trusts | Promoting Good Practice for Safer Care |  | PGPSC Reports LMNS Programme Board reports
|  | 4d.3 |  | Ensure cultural competency training becomes mandatory within each provider trust | LMNS PMO Team | Quality Surveillance |  | Mandatory training compliance - 6 monthly audit of compliance LMNS Programme Board reports Perinatal Quality Surveillance Dashboards
| When investigating serious incidents, consider the impact of culture, ethnicity and language | 4d.4 | Monitoring and reviewing incidents that occur across the LMNS with a focus on culture, ethnicity and language | Ensure ethnicity data is captured for all serious incidents | LMNS PMO Team ICB Quality Team | Quality Surveillance |  | SIs not closed on STEIS unless ethnicity data recorded
|  | 4d.5 |  | Trusts to share PMRT and MBRACCE live reports quarterly at the Perintal Quality Surveillance Meetings | LMNS PMO Trusts | Quality Surveillance |  | Quality Surveillance reports LMNS Programme Board reports
|  | 4d.6 |  | Explore further opportunities to capture the user voice, Introduction of Service User Impact Statements | LMNS PMO Trusts | Quality Surveillance |  | Quality Surveillance reports LMNS Programme Board reports
|  | 4d.7 |  | Triangulate data, including ethnicity and themes from Service User Impact Statements to inform improvments in care provision | LMNS PMO Team Trusts | Quality Surveillance |  | Thematic reviews Quality Surveillance reports LMNS Programme Board

## Priority 4e
Priority 4e: Enablers
Description | [7 empty] | Process indicator
LMS are asked to create the conditions to help achieve equity by: • considering the factors that will support high quality clinical care • working with system partners and the VCSE sector to address the social determinants of health. | [7 empty] | • % of maternity and neonatal staff who attended training about cultural competence in the last two years • % of maternity and neonatal Serious Incidents relating to patient care with a valid ethnic code • % of Perinatal Mortality Review Tool cases with a valid ethnic code
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
| Establish community hubs in the areas with the greatest maternal and perinatal health needs. | 4e.1 |  | Scope feasibility of community hubs in areas with the greatest maternal and perinatal health needs. Identify groups who could best benefit from local hubs | LMNS PMO Team Trusts | LMNS Programme Board |  | LMNS Programme Board reports
|  | 4e.2 |  | Ensure location of community hubs is informed by the geographic distribution of deprivation / minority ethnic populations across Northamptonshire | LMNS PMO Team Trusts | LMNS Programme Board |  | LMNS Programme Board reports
|  | 4e.3 |  | Work with other system partners and VCSE organisations to ensure birthing people and their families can access a range of family orientated services in one place | LMNS PMO Team | LMNS Programme Board |  | LMNS Programme Board reports
| Work with system partners and the VCSE sector to address the social determinants of health. | 4e.4 |  | Hold engagement Events and MVP workshops, linking with faith groups and voluntary sector ensuring use of translation services available | LMNS PMO Team MVP | LMNS Programme Board |  | LMNS Programme Board reports

## Priority 5
Priority 5: Strengthen leadership and accountability
Description | [7 empty] | Process indicator
LMS set out their shared vision in a Local Maternity Transformation Plan in 2017 and should now supplement this with a co-produced equity and equality action plan. The 2021/22 priorities and operational planning guidance: Implementation guidance sets out a two-step process for this: • by 30 November 2021, LMS are asked to submit an equity and equality analysis (covering health outcomes, community assets and staff experience) and a coproduction plan as set out in sub-priority 4a, interventions 1 to 4 • by 30 September 2022, LMS are asked to co-produce equity and equality action plan
Target Date
No. | Action |  | Detail | Actions / Interventions | Responsible Team / organisation | Responsible Workstream | RAG | Monitoring | Comments/Updates | Q3 2022/23 | Q4 2022/23 | Q1 2023/24 | Q2 2023/24 | Q3 2023/24 | Q4 2023/24 | Q1 2024/25 | Q2 2024/25 | Q3 2024/25 | Q4 2024/25 | Q1 2025/26 | Q2 2025/26 | Q3 2025/26 | Q4 2025/26 | Q1 26/27
| To submit an equity and equality analysis (covering health outcomes, community assets and staff experience) and a co-production plan as set out in sub-priority 4a, interventions 1 to 4 | 5.1 | Perinatal Equity and Equality Assessment | Complete Equity and Equiality assessment to include key priorities in the NHSE Equity and Equality Guidance for LMNS. | LMNS PMO Team Trusts | LMNS Programme Board |  | LMNS Programme Board reports
| Develop co produced plan to set out how the NHS will work in partnership to improve equity for women and babies and race equality for staff. The plan should be agreed by the LMNS board and the ICS partnership board and published | 5.2 | Perinatal Equity and Equality Plan | Develop 5 year plan which describes how the LMNS will tackle health inequalities as identified in the Perintal Equity & Equality Assessment | LMNS PMO Team MVP | LMNS Programme Board |  | LMNS Programme Board reports
|  | 5.3 |  | Perinatal Equity and Equality Plan to be signed off by the LMNS Board and the ICS partnership Board | LMNS PMO Team | LMNS Programme Board |  | LMNS Programme Board reports
|  | 5.4 |  | Quarterly review at the nominated groups to take place and the document to be updated as work progresses, new interventions / actions are identified, | LMNS PMO Team | LMNS Programme Board |  | LMNS Programme Board reports

## Communication Plan
Communications Plan
Subject | Key Messages | Audience | Format/Platform? | Target Date(s) | Comments
Awareness of equity and equality analysis and action plan | What is the quality and equality action plan? What has the LMNS done so far to address health inequalities? What is the action plan? How has the action plan been co-produced with women and families? | ICB, acute and primary care providers, women and families, local communities | Email newsletters, social media posts, posters, leaflets | 2022-11-01 | Summary sheet to be prepared and circulated via suggested formats
Easy read analysis document | Where are we now? Where are our areas of need? What are our areas of deprivation? Where are our Voluntary Sector organisations | ICB, acute and primary care providers, women and families, local communities | ICB website, MVP , LMNS website | 2022-11-01 | Summary sheet to be prepared and circulated via suggested formats
Equity & Equality Assessment and 5 year plan to be desktop published | To ensure more user friendly documents with photos | ICB, acute and primary care providers, women and families, local communities | ICB website, MVP , LMNS website | 2022-11-01